## Sheet1
| Name 1 | Name 2 | Name 3 | Name 4
Date | Arpit Mandal - 849420 | Himanshu Dhaka - 849406 | Ashutosh Aneja - 849422 | Arhan Khan -851411 | Overall
3rd Nov | Implemented jwt to medicine stock api, implemented log4net to auth api | Working on MediceStock log4net, swagger and repo pattern implemented | working on Medical representative schedule ( implemented rep schedule table) | Working on PharmacyManagementSystem api , implemented swagger. | Completed few actions of every API and seq diag
2nd Nov | Document read,Flowchart, Worked on Auth Api till token generation and implementing log4net | Document read,Flowchart, working on MedicineStockApi ( created stock list of medicines ) | Document read,Flowchart, working on Medical representative schedule ( fetched doctors information from CSV file) | Document read,Flowchart, Working on PharmacySupplyManagement Api( implemented demand supply action) | Completed few actions of every API and made workflow diag